## Sheet1
TASK | START | END | Completed (Yes/No)
Sprint 1: Week 1 - 11/2/23 | 2023-11-02 | 2023-11-03
Post-RSVP: Discussed painpoints with team & BBBSEM
CEE to CRS: (same as above)
Inquiry Form: Study inquiry form and hypothesize reccomendations
Pre-Interview Comms: Simultaneously review emails and brainstorm edits
Post-interview Comms:
Post-Interview Engagement: Talk to important stakeholders and work on drafting ideas to explore
Sprint 2: Week 2 - 11/6/23 | 2023-11-06 | 2023-11-10
Post-RSVP: Connect with Jesse, define issue
CEE to CRS: Connect with Aka & Rebecca, define issue (point of communication, frequency)
Inquiry Form: Draft revisions
Pre-Interview Comms: Conduct expert interview with Kathryn
Post-interview Comms:
Post-Interview Engagement: Review information provided by Terry and turn these into actual hypotheses
Sprint 3: Week 3 - 11/13/23 | 2023-11-13 | 2023-11-17
Post-RSVP: Brainstorm ways to alter CEE Form
CEE to CRS: Brainstorm ways to streamline handoff
Inquiry Form:
Pre-Interview Comms: Utilize Kathryn's insights in drafting revisions organize finalized reccomendations and suggestions
Post-interview Comms:
Post-Interview Engagement: Test out hypothesis by speaking to experts or gathering more data on best practices
Sprint 4: Week 4 - 11/20/23 | 2023-11-20 | 2023-11-24
Post-RSVP: Work through implementation, receive feedback (IUCG & BBBSEM)
CEE to CRS: (same as above)
Inquiry Form: Organize finalized reccomendations and suggestions
Pre-Interview Comms:
Post-interview Comms:
Post-Interview Engagement: Convert hypothses into key recommendations
Sprint 5: Week 5 - 11/27/23 - Final Deliverable Creation | 2023-11-27 | 2023-12-01
Post-RSVP: Potential A/B Testing on Volunteers, Document Changes made
CEE to CRS: (same as above)
Inquiry Form:
Pre-Interview Comms:
Post-interview Comms:
Post-Interview Engagement: Work on final deliverable presentation while making changes as needed
Sprint 6: Week 6 - 12/4/23 - Final Deliverable | 2023-12-04 | 2023-12-08
Post-RSVP: Compile, present changes. Recognize effects on conversion rate
CEE to CRS: (same as above)
Inquiry Form:
Pre-Interview Comms:
Post-interview Comms:
Post-Interview Engagement: Finalize deliverable and practice presentation